## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Connectify – Professional Networking Platform |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IAC IP23 React JS
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-08-12 | Frequent component rerendering affected application performance. | Performance | Yes | Optimize rendering using React memoization techniques. | Implemented Redux state management and optimized component updates. | Adib Afsar | Solved | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
2 | 2024-08-25 | Designing Firestore collections for scalable real-time features was challenging. | Database Design | Yes | Plan schema before development. | Refactored collections into articles and profiles. | Adib Afsar | Solved
3 | 2024-09-10 | Real-time comments and notifications increased read operations. | Architecture | Yes | Minimize unnecessary reads and structure data efficiently. | Redesigned data flow and optimized queries. | Adib Afsar | Solved
4 | 2024-09-18 | Managing global state across multiple modules became complex. | State Management | Yes | Use centralized state management. | Implemented Redux and Redux Thunk. | Adib Afsar | Solved
5 | 2024-10-05 | Firebase Storage access restrictions interrupted media retrieval. | Cloud Services | Yes | Monitor Firebase policy updates and billing changes. | Enabled Blaze plan and updated permissions. | Adib Afsar | Solved
6 | 2024-10-12 | Firestore security rules expired unexpectedly. | Security | Yes | Regularly review Firebase rules. | Updated Firestore rules and validated permissions. | Adib Afsar | Solved
7 | 2024-10-20 | Deployment issues occurred due to environment configuration differences. | Deployment | No | Verify production configurations before release. | Updated deployment settings on Vercel. | Adib Afsar | Solved
8 | 2024-10-25 | Documentation was difficult to prepare after development completion. | Project Management | No | Maintain documentation throughout the project lifecycle. | Created documentation templates and updated them regularly. | Adib Afsar | Solved