## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Connectify – Professional Networking Platform
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 07-28-2024
EXPECTED COMPLETION DATE | 10-28-24
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | Develop a professional networking platform that enables students and working professionals to build connections, share content, discover job opportunities, and communicate in real time.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Existing professional networking solutions can be complex and fragmented. Connectify provides a centralized platform for networking, job discovery, messaging, and user engagement using a simple and intuitive interface.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | • Implement secure Google Authentication. • Enable profile creation and management. • Support post creation, likes, comments, and saved posts. • Implement real-time messaging. • Enable job posting and keyword-based search. • Achieve successful deployment on Vercel. • Ensure responsive design across devices.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | • Source code repository • Software Requirement Specification (SRS) • Software Design Specification (SDS) • Work Breakdown Structure (WBS) • Project Schedule • RAID Log • Test Plan and Reports • Traceability Matrix • Deployment URL • Demo Video • Project Report
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | • Google Authentication • User profiles • Connections and follow functionality • Posts, likes, comments, and saved posts • Real-time messaging • Notifications • Job posting and search • Image uploads using Firebase Storage
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | • Native mobile applications • Push notifications • Payment integration • AI-based recommendations • Third-party recruitment platform integration • Offline functionality
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 Resource – Adib Afsar (React JS Intern)
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | • Cloud Counselage mentors • Firebase services • GitHub • Vercel hosting • Visual Studio Code
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Project developed as part of internship program using free-tier cloud services. No direct development cost incurred.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | ADIB AFSAR
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | • Cloud Counselage Pvt. Ltd. • Domain Lead • Students • Working Professionals • Recruiters
END CUSTOMER (Mention the client name.) | Students, working professionals, and recruiters.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | • Firebase pricing changes • Real-time synchronization issues • Performance issues due to unnecessary rerenders • Third-party service downtime
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | • Users have internet connectivity. • Users possess Google accounts. • Firebase services remain available.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | • Three-month internship timeline • Firebase free-tier limitations • Limited development resources
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 2024-10-08
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 08-20-2024
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 2024-05-09
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 2024-10-10
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 10-20-2024
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 10-25-2024
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 10-28-2024