## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Global Professional Internship - React JS Project Schedule
|  | PROJECT START DATE | 2024-07-28
|  | Display Week Sr No | 1 | [10 empty] | 2024-07-22 | [6 empty] | 2024-07-29 | [6 empty] | 2024-08-05 | [6 empty] | 2024-08-12 | [6 empty] | 2024-08-19 | [6 empty] | 2024-08-26 | [6 empty] | 2024-09-02 | [6 empty] | 2024-09-09 | [6 empty] | 2024-09-16
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 2024-07-22 to 2024-09-22
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2024-07-22 to 2024-09-22
1 | Week 1 – Requirement Analysis | Requirement Gathering | Understand problem statement |  | None | Adib Afsar | 2024-07-28 | 2024-08-03 | 2024-08-03 | 20 | Completed | 100% | Completed
1.1 |  | Research | Analyze LinkedIn features |  | None | Adib Afsar | 2024-07-29 | 2024-07-31 | 2024-07-31 | 10 | Completed | 100% | Completed
1.2 |  | Planning | Define feature list |  | 1.1 | Adib Afsar | 2024-08-01 | 2024-08-03 | 2024-08-03 | 10 | Completed | 100% | Completed
2 | Week 2 – UI Design | UI/UX Design | Design pages and components |  | 1 | Adib Afsar | 2024-08-04 | 2024-08-10 | 2024-08-10 | 25 | Completed | 100% | Completed
3 | Week 3 – Authentication | Authentication Module | Implement Google login |  | 2 | Adib Afsar | 2024-08-11 | 2024-08-17 | 2024-08-17 | 20 | Completed | 100% | Completed
4 | Week 4 – Profile Module | User Profiles | Create and edit profiles |  | 3 | Adib Afsar | 2024-08-18 | 2024-08-24 | 2024-08-24 | 30 | Completed | 100% | Completed
5 | Week 5 – Articles | Feed Module | Create posts and display feed |  | 4 | Adib Afsar | 2024-08-25 | 2024-08-31 | 2024-08-31 | 30 | Completed | 100% | Completed
5.1 |  | Engagement | Implement likes and comments |  | 5 | Adib Afsar | 2024-09-01 | 2024-09-05 | 2024-09-05 | 20 | Completed | 100% | Completed
6 | Week 6 – Connections | Follow System | Follow and unfollow users |  | 5 | Adib Afsar | 2024-09-06 | 2024-09-12 | 2024-09-12 | 20 | Completed | 100% | Completed
7 | Week 7 – Messaging | Chat Module | Real-time messaging |  | 6 | Adib Afsar | 2024-09-13 | 2024-09-20 | 2024-09-20 | 30 | Completed | 100% | Completed
8 | Week 8 – Notifications | Notification Module | Engagement notifications |  | 7 | Adib Afsar | 2024-09-21 | 2024-09-28 | 2024-09-28 | 20 | Completed | 100% | Completed
9 | Week 9 – Jobs | Job Module | Job posting and search |  | 8 | Adib Afsar | 2024-09-29 | 2024-10-06 | 2024-10-06 | 25 | Completed | 100% | Completed
10 | Week 10 – Media Upload | Storage Module | Image upload functionality |  | 9 | Adib Afsar | 2024-10-07 | 2024-10-12 | 2024-10-12 | 15 | Completed | 100% | Completed
11 | Week 11 – Testing | QA and Debugging | Fix bugs and optimize UI |  | 10 | Adib Afsar | 2024-10-13 | 2024-10-20 | 2024-10-20 | 25 | Completed | 100% | Completed
12 | Week 12 – Deployment | Hosting and Documentation | Deploy to Vercel and prepare reports |  | 11 | Adib Afsar | 2024-10-21 | 2024-10-28 | 2024-10-28 | 25 | Completed | 100% | Completed

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2020-01-01
PROJECT END DATE | 2020-01-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1